## Sheet1
SEVERITY
Risk | Result | Response | Likelihood | Impact | Risk Level | Date of RS | Revisited | Comments |  |  | Minimal | Minor | Moderate | Major | Severe
Hardware failure or Software) | Hardware fails or software is corrupt | Have other hardware available, back up for data and other software | Likely | Servere | 15 | 2021-04-27 | 04/05/2021 & 20/5/2021 | Laptop software installed incorrectly | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
Software failure | App refused to connect to GCP VM so I was unable to do test in venv | Try creating other VM and copies of App | Likely | Servere | 15 | 2021-04-27 | 21/05/21 & 23/5/21 | Unable to do Testing integration in venv |  | Expected | 4 | 8 | 12 | 16 | 20
Accidental human interference | Accidentally deleting files | Configure permissions properly and back up regularly | Likely | Major | 12 | 2021-04-27 | 2021-05-19 | Creating a DB in Workbench |  | Likely | 3 | 6 | 9 | 12 | 15
DDOS Attack | Causes a denial of service for users, i.e. unabvle to log in the app | Configure the firewall properly and have good DDOS mitigation | Possible | Servere | 10 | 2021-04-27 | 2021-05-23 | Recreated new venv and new firewalls |  | Possible | 2 | 4 | 6 | 8 | 10
Users forget passwords | User won't be able to login | Recover your password options | Guaranteed | Minimal | 5 | 2021-04-27 | 30/4/2021 & 20/05/2021 | Too many passwords |  | Unlikely | 1 | 2 | 3 | 4 | 5
Data leakage/theft | Access to database | Access to database managed by multifactor authentication | Possible | Servere | 10 | 2021-04-27
User passwords can be guessed or cracked | Hacker will have access to user's information | Password policy in place(must have letters, numbers and symbols…) | Possible | Minor | 4 | 2021-04-27 | 2021-05-17 | No way I can cracke it
Data Encryption | Data will be exposed | Make sure app connects to web services using secure connection protocols such as HTTPS. | Possible | Moderate | 6 | 2021-04-27
Apps new features released | Denied access to Repo from Git Bash | Re-installed or update the app | Likely | Moderate | 9 | 2021-04-27 | 2021-05-22 | Unable to push to repo due to Credential Manager in GitHub

## Sheet2
Data Encryption | Data will be exposed | Make sure app connects to web services using secure connection protocols such as HTTPS. | Possible | Moderate | 6 | 2021-04-27
Apps new features released | Denied access to Repo from Git Bash | Re-installed or update the app | Likely | Moderate | 9 | 2021-04-27 | 2021-05-22 | Unable to push to repo due to Credential Manager in GitHub